## Action Plan
Action Plan
Ministry Strategy Objective: Re-Envision Groups Strategy |  |  | Team Leader: | [12 empty] | Date Created:
Team: | [15 empty] | Next Review:
Background: The Christian life is meant to be lived in community. We need a groups strategy that provides genuine life-on-life fellowship and enhances understanding of Scripture and a focus on praying for one another. This is the primary vehicle for discipleship growth.
Alignment with Vision Indicator & Vision Breakthrough: |  |  | Timeline | [12 empty] | Status Red, Yellow, Green
[5 empty] | = Original Plan |  |  |  | x | = Complete
Planned Complete Date
Action Step | Owner | Deliverable |  | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
PHASE 1: EVALUATION & PLANNING
Craft a 1 Paragraph "vision" for the ideal groups strategy |  | Completed Paragraph
Complete Group Evaluation for each existing Group/Class |  | Completed Evaluation Report
Determine Future for Existing Groups |  | Decision Matrix
Research & Select Curriculum/Content |  | Brief Curriculum/Contnet Report
Research Leader Training Options |  | Brief Leadership Training Report
Outline Function & Types of New Groups |  | New Groups Proposal
Set Target Number of New Groups & Leaders |  | New Groups Proposal
Develop a Target Launch Date & Schedule for New Groups |  | New Groups Proposal
Determine Budget Implications for New Groups Strategy |  | Budget Proposal
Draft plan for leader recruitment & training |  | Phase 2 Action Plan