## Action Plan
Action Plan
Ministry Strategy Objective: Outreach Strategy |  |  | Team Leader: | [12 empty] | Date Created:
Team: | [15 empty] | Next Review:
Background: Our church will only be fruitful when every person is actively sharing their faith outside of the church walls. Our outreach strategy empowers us to act individually and collectively to impact our community with the Gospel.
Alignment with Vision Indicator & Vision Breakthrough: |  |  | Timeline | [12 empty] | Status Red, Yellow, Green
[5 empty] | = Original Plan |  |  |  | x | = Complete
Planned Complete Date
Action Step | Owner | Deliverable |  | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
PHASE 1: EVALUATION & PLANNING
Craft a 1 Paragraph "vision" for the ideal outreach strategy |  | Completed Paragraph
Identify your "Jerusalem" - set "soft boundaries" |  | Map with outlined geography
Conduct demographics study |  | Demographics report
Conduct Community Needs Survey |  | Survey Report
Meet with Community Leaders to Determine Needs |  | Meeting Reports
Select Evangelism Training Curriculum |  | Curriculum/Training Report
Review 5 D's - Select Primary Outreach Focus |  | Outreach Proposal
Craft plan for Outreach Events |  | Outreach Proposal
Determine any Outreach Partners |  | Outreach Proposal
Collaborate with Growth Step for Evangelism Training |  | Outreach Proposal
Review Budget Implications for Outreach |  | Budget Proposal
Draft timeline for Outreach Events & evangelism training |  | Phase 2 Action Plan