## Action Plan
Action Plan
Ministry Strategy Objective: Improve Guest Experience |  |  | Team Leader: | [12 empty] | Date Created:
Team: | [15 empty] | Next Review:
Background: The guest experience is central to engaging people in the discipleship pathway process. This project seeks to improve how we connect with newcomers and integrate them into discipleship.
Alignment with Vision Indicator & Vision Breakthrough: |  |  | Timeline | [12 empty] | Status Red, Yellow, Green
[5 empty] | = Original Plan |  |  |  | x | = Complete
Planned Complete Date
Action Step | Owner | Deliverable |  | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
PHASE 1: EVALUATION & PLANNING
Craft a 1 Paragraph "vision" for the ideal guest experience |  | Completed Paragraph
Review 3 comparable churches' first-time guest process |  | Brief report on each church
Complete Church Website & Social Media Evaluation |  | Completed Evaluation Report
Complete Grounds, Parking, & External Signage Evaluation |  | Completed Evaluation Report
Complete Facility & Internal Signage Evaluation |  | Completed Evaluation Report
Complete Welcome & Guest Connection Area Evaluation |  | Completed Evaluation Report
Complete Children's Ministry Area Evaluation |  | Completed Evaluation Report
Complete Worship Service Evaluation |  | Completed Evaluation Report
Complete Guest Follow-up Process Evaluation |  | Completed Evaluation Report
Prioritize Action Items from Evaluation Results |  | Guest Experience Project proposal
Assign Action Items & Due Dates |  | Updated Phase 2 Action Plan
Solicit bids from 3rd party vendors (if necessary) |  | Bids report
Create a Guest Experience implementation budget |  | Budget proposal